## Front end
E- FAM APP DEVELOPMENT PROJECT PLAN
Category | Area | Status as at 3 /1/16 | Owner | Responsible | Comments | Reviewers | Approvers | By (Date) | Status | Pass/Fail
Creative | Logo image and menu | Done | Bob | Bob | Done | Y | Y |  | Closed | Pass
| Customer Journey | Design flow |  | Bob
| Content and Copy | Most of it done but needs to be give a final round | Kevin | Sharon | To review once the final wireframe is done | Y | N |  | TBC
| Wireframe | Almost done | Kevin | Bob | Final screenshots need to be done so we have a master document fo sign off | Y | N | TBA | WIP
App Development | Creative design | Logo image on the menu to be adapted to adjust to different screens/phones | Carol | Bob
| My Orders | In my orders refining the order processing to three levels from the previous 5 |  | Bob | To have a look at this current layout | Y | Y |  | Clode | Pass
| Purchase | Purchase via loyalty points will be introduced in V2 |  | Bob | To please review current layout of loyalty points to be enhanced | Y | Y |  | Closed | Pass
| My Info | My info button edit page save button needs to be adjusted |  | Carol | Done | Y | Y |  | Closed | Pass
| T&Cs | Terms section the disclaimer section appears not to be fitting in the page needs to be adjusted |  | Bob |  | Y | Y |  | Closed | Pass
| User Guide | Still pending |  | Bob | This will be done once the overall look and feel has been completed and signed off | Y | N |  | WIP
| Inventory Loader | Not yet done |  | Bob | It needs to be addressed as per layout. WIP | Y | N |  | WIP
|  | Loader GIF image is yet to be done |  | Bob | Creative to kindly share as we need this from creative to finalize
| Navigation buttons | To be adjusted so that they are evenly laid out on the bottom of the screen |  | Carol | Not yet done | Y | N |  | WIP
|  | They need to adapt to the screen size of different phones |  | Carol | To retain consistency all through | Y | N |  | WIP
| My Cart | Has black transition in the counter pick up page |  | Carol | Not done | Y | N |  | Not done
| Next Button | To be centered to present an appealing layout |  | Bob | Done | Y | Y |  | Closed
| Product Page | Description of weight needs to be aligned to the left, |  | Carol
|  | increase the size of the button for easier addition and reduction of goods |  | Carol | Done. New request to be done for the f ront end | Y | N |  | To be done
| Collection | The icon appears abit smaller this needs to be adjusted to the required size |  | Carol | Initial request done. New edit to be worked on | Y | N |  | To be done
| Payment Page | Font looks different need to adjust to standard layout |  | Carol | Font style is the same, size is different in different pages. Needs to be consistent | Y | N |  | To be done
| Receipt Page- Cash on delivery | Done |  | Carol | Closed | Y | Y |  | Closed
| Receipt Page- Pay now | Done |  | Carol | Closed | Y | Y |  | closed
| Close page | Not yet done. Needs to adapt new design |  | Carol | Needs to be adjusted as described in the layout | Y | N
| Exit Button | Done |  | Carol | Done | Y | Y |  | Closed
| Payment Button | New request to be worked on. |  | Carol | To work on it a fresh | Y | N |  | To be done
| Past Orders - re order button | Restrusture of the offering to be done |  | Carol | This exercise will be carried out as last function | Y | N
| Locations | Entry of all the locations similar to Yum current locations. Not completely showing |  | Carol | To be improved | Y | N |  | WIP
| Category Description | Entry of all the product categories described to be worked on. Not completely showing |  | Carol | To be improved | Y | N |  | WIP
| My Info page | Select gender - to be worked on - font size is small |  | Carol | To be improved | Y | N |  | WIP
| Talk to us icon | White space to be removed from the layot |  | Carol | To be improved | Y | N |  | WIP
| My Adress icon | Done |  | Carol | To edit | Y | Y |  | Closed
| Login message | Done |  | Carol |  | Y | Y |  | Closed
| Exit Notification | Exit notification customized button |  | Carol | To be customised | Y | N |  | To be done
| Payment icon | Addition of payment icons in the credit processing page - Done |  | Carol | Done an | Y | Y |  | Closed
| Admin | Admin restrict access to specific supermarket
Admin and Client cancel functions of orders
| Orders | Order verification by item - Revised To Feedback Form
| Address Section | Longitude and longitude code – Revised To Added More Information On The Address Section |  | Carol | Done | Y | Y |  | Closed
| Yum API | YUM API integrating it with our system
| SMS & Email | Install sms & email notification gateway
| My address Icon | My address icon, my information icon looks rough around the edges they need to been rounded properly |  | Carol | Done | Y | Y |  | Closed
| My information icon | Icon looks faint needs to be abit darker |  | Carol | Nt Done | Y | N |  | WIP
| Information Bar | Once you have selected the gender it needs to be displayed |  | Carol | Done | Y | Y |  | Closed
| Address Information | To be renamed to e.g. CBD AREA, GIGIRI AREA and remove ENVIRONS when you are selecting your neighborhood, but this naming protocol of + ENVIRONS should rename when selecting neighborhood when you want to shop |  | Carol | Done | Y | Y |  | Closed
|  | Change the hint to distinguishable feature in the neighborhood |  | Carol | Done | Y | Y |  | Closed
|  | Change hint to briefly describe the direction up to your home |  | Carol | Done | Y | Y |  | Closed
|  | Change Hint to Road Name/Matatu Number |  | Carol | Done | Y | Y |  | Closed
|  | Make Neighborhood area and road name compulsory |  | Carol | Done | Y | Y |  | Closed
| Saving Feature | Currently saving feature is not working for my address information |  | Carol | Done | Y | Y |  | Closed
| Talk to us icon | To be connected to the official cell phone number and official email we are going to provide shortly |  | Carol | Email ad and Phone number t be assigned suport@e-fam.com / 0700665180 | Y | N |  | WIP
| Copy | Check the grammar for the isle i) Remove (s) from frozen foods ii) Remove (s) from seafoods |  | Carol | Done | Y | Y |  | Closed
| Cart / Products | There is a slight confusion in the addition of products into the cart and the actual cart layout, on observation they look exactly alike , we need to slightly adjusted the element s in how to add to cart |  | Carol | New request. To be worked on | Y | N |  | WIP
|  | When you are in your cart, the pay button need to be highlighted and we need to rename this button as PROCEED because the next page is not about paying its about delivery options/counter pick up |  | Carol | To be discussed in next meeting
| Counter Picking | The counter pickup into payments option there is still a black transitions |  |  | To be discussed in next meeting
| Payment | Pay now into using credit card there is a black transition |  |  | To be discussed in next meeting
|  | Pay now into using mobile money there is a black transition |  |  | To be discussed in next meeting
|  | In the payment via mobile phone please delete that option number one in the payments instruction because this number we had already verified before, Use the number that we had verified before as the default number that shows up in the mobile section window just above process payment |  |  | To be discussed in next meeting
| Delivery | In the delivery options page, home delivery the select address icon need to be replaced with the address icon and the address icon also needs to appear next to all the available address options. There should be an edit & delete buttons next to the available addresses |  |  | To be discussed in next meeting
|  | There should also an add address option on top of this page |  |  | To be discussed in next meeting
Check the loading time for when you are using pay now there is a short delay
Website | Look and feel | WIP - should be finalised soon. | Dan | Dan | Almost done | N | N | 2016-04-02 | WIP | TBC
| Copy | To be done once website is handed over | Dan | Sharon | To take over after Thursday | N | N
Menus
Mobile | Look and feel | To be done once web version is completed | Dan | Dan | Finalising on Web version | N | N | Next week |  | TBA
Testing | On Android device | To be done once back end and front end is completed | Kevin | ALL
Launch | Venue | Yet to be identified | Kevin | Shella
| Launch concept | To be briefed in once a partner / supermarket is identified and approved, | Kevin | Shella
| Partner supermarket | Yet to be identified. | Shella | Shella
| Launch invites | Details to be firmed up once app is almost ready | Kevin | Shella
| PR Startegy | To be thought of. Team to decide best partner to work with. | Kevin | Betty
| Social media | The pages to be designed and managed by RH. Count | Kevin | Jayson
|  | Work out an online launch plan | Kevin | Jayson
| FB | To be created | Kevin | Jayson | done
| Twitter | To be created | Kevin | Jayson | done
| IG | To be created | Kevin | Jayson | done
| Youtube | To be created | Kevin | Jayson | done
For public launch, required. The May 12 solution, so possibly later. Production minus 2 weeks (for us to UAT).
For public launch, required. The May 12 solution, so possibly later. Production minus 2 weeks (for us to UAT).
For public launch, required. The May 12 solution, so possibly later. Production minus 2 weeks (for us to UAT).
The tablet. We can provision manually if we have access to BSS.
agent transaction queries
Reports
(add these to the catalog)
For launch: One tool for telephony; and separate banking solution Not launch critical (where do we park this) Strategic end to end solution??